## Dashboard
SWP391 - SU26SWP05 3-Sprint Function-Based Plan
Project | Manga Creation Workflow and Publishing Management System |  | Metric | Value
Team | Hiền, Hào, Dũng, Phát |  | Total Functions | 72
Sprint Style | 3 sprint groups based on main project functions |  | Done | 0
Sprint Count | 3 |  | In Progress | 0
Owner Columns | Blank for team to select manually |  | To Do | 72
Method | Agile / Scrum |  | Completion | 0%
Core Flow | Series → Chapter → Page Workspace → Task → Submission → Review → Publishing → Ranking → Decision |  | Blank Main Owner | 72
Sprint | Module / Function | Total Functions | Done | Completion
Sprint 1 | Core Foundation, Series & Chapter | 19 | 0 | 0%
Sprint 2 | Page Workspace, Task Assignment & Review Workflow | 36 | 0 | 0%
Sprint 3 | Publishing, Ranking, Risk Decision & Final Demo | 17 | 0 | 0%

## Sprint Plan
Sprint | Module / Function | Included Functions | Demo Goal
Sprint 1 | Core Foundation, Series & Chapter | Authentication, User/Role Management, Series Proposal, Proposal Approval, Series Management, Chapter Management, Page Upload | User can login, Mangaka creates a series proposal, Board approves it, and Mangaka creates chapter with uploaded pages
Sprint 2 | Page Workspace, Task Assignment & Review Workflow | Page Workspace, Region Segmentation, Task Assignment, Assistant Submission, Mangaka Review, Revision, Editor Review, Annotation | Mangaka creates regions, assigns tasks, Assistant submits work, Mangaka reviews, and Editor reviews chapter
Sprint 3 | Publishing, Ranking, Risk Decision & Final Demo | Publishing Schedule, Final Approval, Vote Import, Ranking Dashboard, Risk Alert, Board Decision, Testing, Demo Data, Report/Slide | Board publishes chapter, imports votes, system calculates ranking, creates risk alert, and Board makes decision

## Backlog
Function ID | Sprint | Function | Description | Main Owner | Support | Priority | Status | Module
S1-F01 | Sprint 1 | Login | User can log in using valid email and password |  |  | High | To Do | Authentication
S1-F02 | Sprint 1 | Logout | User can log out from the system |  |  | High | To Do | Authentication
S1-F03 | Sprint 1 | Role-based Dashboard | System redirects user to the correct dashboard based on role |  |  | High | To Do | Authorization
S1-F04 | Sprint 1 | User Management | Admin can create, update, deactivate users |  |  | Medium | To Do | Administration
S1-F05 | Sprint 1 | Role Management | Admin can assign roles to users |  |  | Medium | To Do | Administration
S1-F06 | Sprint 1 | Create Series Proposal | Mangaka can create a new series proposal |  |  | High | To Do | Series Proposal
S1-F07 | Sprint 1 | Edit Series Proposal | Mangaka can edit proposal before submission |  |  | Medium | To Do | Series Proposal
S1-F08 | Sprint 1 | Upload Sample Manuscript | Mangaka can upload sample manuscript for proposal |  |  | High | To Do | Series Proposal
S1-F09 | Sprint 1 | Submit Proposal | Proposal can be submitted for approval |  |  | High | To Do | Series Proposal
S1-F10 | Sprint 1 | Proposal Review | Editor or Board can view proposal detail |  |  | High | To Do | Proposal Approval
S1-F11 | Sprint 1 | Approve / Reject Proposal | Board can approve or reject proposal |  |  | High | To Do | Proposal Approval
S1-F12 | Sprint 1 | Create Series from Approved Proposal | System creates official series after approval |  |  | High | To Do | Series Management
S1-F13 | Sprint 1 | Series List | User can view list of series |  |  | High | To Do | Series Management
S1-F14 | Sprint 1 | Series Detail | User can view series information and related chapters |  |  | High | To Do | Series Management
S1-F15 | Sprint 1 | Create Chapter | Mangaka can create a chapter for an active series |  |  | High | To Do | Chapter Management
S1-F16 | Sprint 1 | Chapter List | User can view chapter list by series |  |  | High | To Do | Chapter Management
S1-F17 | Sprint 1 | Chapter Detail | User can view chapter progress, deadline and page list |  |  | High | To Do | Chapter Management
S1-F18 | Sprint 1 | Upload Manga Page | Mangaka can upload manga pages for a chapter |  |  | High | To Do | Page Management
S1-F19 | Sprint 1 | Page List | User can view pages inside a chapter |  |  | Medium | To Do | Page Management
S2-F01 | Sprint 2 | Open Page Workspace | Mangaka can open workspace for a selected page |  |  | High | To Do | Page Workspace
S2-F02 | Sprint 2 | Display Manga Page Canvas | System displays manga page on canvas |  |  | High | To Do | Page Workspace
S2-F03 | Sprint 2 | Zoom / Fit Page | User can zoom in, zoom out and fit page |  |  | Medium | To Do | Page Workspace
S2-F04 | Sprint 2 | Draw Region | Mangaka can draw a rectangle region on the page |  |  | High | To Do | Region Segmentation
S2-F05 | Sprint 2 | Select Region Type | Mangaka can select type: panel, character, background, bubble |  |  | High | To Do | Region Segmentation
S2-F06 | Sprint 2 | Save Region Coordinates | System saves x, y, width, height and region type |  |  | High | To Do | Region Segmentation
S2-F07 | Sprint 2 | Edit / Delete Region | Mangaka can edit or delete a region |  |  | Medium | To Do | Region Segmentation
S2-F08 | Sprint 2 | AI Suggest Region | AI can suggest regions on page, optional |  |  | Low | To Do | AI Optional
S2-F09 | Sprint 2 | Create Task from Region | Mangaka can create task from selected region |  |  | High | To Do | Task Management
S2-F10 | Sprint 2 | Assign Task to Assistant | Mangaka can assign task to an Assistant |  |  | High | To Do | Task Management
S2-F11 | Sprint 2 | Task Detail | User can view task detail and region information |  |  | High | To Do | Task Management
S2-F12 | Sprint 2 | Task Board | User can view tasks by status on kanban board |  |  | Medium | To Do | Task Management
S2-F13 | Sprint 2 | My Assigned Tasks | Assistant can view tasks assigned to them |  |  | High | To Do | Task Management
S2-F14 | Sprint 2 | Task Status Tracking | System tracks Assigned, In Progress, Submitted, Revision, Approved |  |  | High | To Do | Task Management
S2-F15 | Sprint 2 | Task Notification | Assistant receives notification when task is assigned |  |  | Medium | To Do | Notification
S2-F16 | Sprint 2 | View My Tasks | Assistant can view assigned task list |  |  | High | To Do | Assistant Submission
S2-F17 | Sprint 2 | View Task Detail | Assistant can view task instruction and deadline |  |  | High | To Do | Assistant Submission
S2-F18 | Sprint 2 | Download Reference File | Assistant can download page or reference files |  |  | Medium | To Do | Assistant Submission
S2-F19 | Sprint 2 | Upload Submission | Assistant can upload completed task file |  |  | High | To Do | Assistant Submission
S2-F20 | Sprint 2 | Add Submission Note | Assistant can add note when submitting |  |  | Medium | To Do | Assistant Submission
S2-F21 | Sprint 2 | Submission Version History | System stores multiple submission versions |  |  | Medium | To Do | Assistant Submission
S2-F22 | Sprint 2 | Submission Notification | Mangaka receives notification when submission is uploaded |  |  | Medium | To Do | Notification
S2-F23 | Sprint 2 | Pending Submission List | Mangaka can view submissions waiting for review |  |  | High | To Do | Mangaka Review
S2-F24 | Sprint 2 | Submission Preview | Mangaka can preview Assistant submission |  |  | High | To Do | Mangaka Review
S2-F25 | Sprint 2 | Compare Original / Submission | Mangaka can compare original page and submitted file |  |  | Medium | To Do | Mangaka Review
S2-F26 | Sprint 2 | Approve Submission | Mangaka can approve accepted submission |  |  | High | To Do | Mangaka Review
S2-F27 | Sprint 2 | Request Revision | Mangaka can request revision if submission is not accepted |  |  | High | To Do | Mangaka Review
S2-F28 | Sprint 2 | Review Comment | Mangaka must write comment when requesting revision |  |  | High | To Do | Mangaka Review
S2-F29 | Sprint 2 | Update Chapter Progress | System updates chapter progress after task approval |  |  | High | To Do | Chapter Progress
S2-F30 | Sprint 2 | Chapter Ready for Review List | Editor can view chapters ready for review |  |  | High | To Do | Editor Review
S2-F31 | Sprint 2 | Editor Review Screen | Editor can review chapter pages and manuscript |  |  | High | To Do | Editor Review
S2-F32 | Sprint 2 | Add Annotation | Editor can add annotation on page |  |  | High | To Do | Annotation
S2-F33 | Sprint 2 | Annotation Type | Editor can classify annotation type |  |  | Medium | To Do | Annotation
S2-F34 | Sprint 2 | Approve Chapter | Editor can approve reviewed chapter |  |  | High | To Do | Editor Review
S2-F35 | Sprint 2 | Send Revision to Mangaka | Editor can request Mangaka revision |  |  | High | To Do | Editor Review
S2-F36 | Sprint 2 | Review History | System stores editor review history |  |  | Medium | To Do | Editor Review
S3-F01 | Sprint 3 | Publication Schedule | Board can create publication schedule |  |  | Medium | To Do | Publishing
S3-F02 | Sprint 3 | Final Approval | Board can final approve chapter |  |  | Medium | To Do | Publishing
S3-F03 | Sprint 3 | Lock Final Version | System locks final version after approval |  |  | Medium | To Do | Publishing
S3-F04 | Sprint 3 | Import Vote Data | Board can import reader vote data |  |  | Medium | To Do | Voting
S3-F05 | Sprint 3 | Validate Vote Data | System validates vote data |  |  | Medium | To Do | Voting
S3-F06 | Sprint 3 | Calculate Ranking | System calculates ranking by vote data |  |  | Medium | To Do | Ranking
S3-F07 | Sprint 3 | Ranking Dashboard | User can view ranking dashboard |  |  | Medium | To Do | Ranking
S3-F08 | Sprint 3 | Ranking History | User can view ranking history by issue |  |  | Low | To Do | Ranking
S3-F09 | Sprint 3 | Risk Alert | System creates alert when ranking is low |  |  | Medium | To Do | Risk Decision
S3-F10 | Sprint 3 | Risk Alert Detail | Board can view detail of ranking risk |  |  | Medium | To Do | Risk Decision
S3-F11 | Sprint 3 | Series Dossier | Board can view series dossier before decision |  |  | Medium | To Do | Risk Decision
S3-F12 | Sprint 3 | Board Decision | Board can choose Continue, Cancel, or Change Schedule |  |  | Medium | To Do | Risk Decision
S3-F13 | Sprint 3 | Update Series Status | System updates series status after board decision |  |  | Medium | To Do | Risk Decision
S3-F14 | Sprint 3 | Full System Testing | Team tests the full end-to-end workflow |  |  | High | To Do | Testing
S3-F15 | Sprint 3 | Bug Fixing | Team fixes critical bugs before final demo |  |  | High | To Do | Testing
S3-F16 | Sprint 3 | Demo Data | Prepare accounts, series, chapters, pages, tasks, submissions, ranking data |  |  | High | To Do | Demo
S3-F17 | Sprint 3 | Final Report / Slide | Complete final report and presentation slide |  |  | High | To Do | Documentation

## Functions by Sprint
Sprint | Module / Function | Functions
Sprint 1 | Core Foundation, Series & Chapter | - Login - Logout - Role-based Dashboard - User Management - Role Management - Create Series Proposal - Edit Series Proposal - Upload Sample Manuscript - Submit Proposal - Proposal Review - Approve / Reject Proposal - Create Series from Approved Proposal - Series List - Series Detail - Create Chapter - Chapter List - Chapter Detail - Upload Manga Page - Page List
Sprint 2 | Page Workspace, Task Assignment & Review Workflow | - Open Page Workspace - Display Manga Page Canvas - Zoom / Fit Page - Draw Region - Select Region Type - Save Region Coordinates - Edit / Delete Region - AI Suggest Region - Create Task from Region - Assign Task to Assistant - Task Detail - Task Board - My Assigned Tasks - Task Status Tracking - Task Notification - View My Tasks - View Task Detail - Download Reference File - Upload Submission - Add Submission Note - Submission Version History - Submission Notification - Pending Submission List - Submission Preview - Compare Original / Submission - Approve Submission - Request Revision - Review Comment - Update Chapter Progress - Chapter Ready for Review List - Editor Review Screen - Add Annotation - Annotation Type - Approve Chapter - Send Revision to Mangaka - Review History
Sprint 3 | Publishing, Ranking, Risk Decision & Final Demo | - Publication Schedule - Final Approval - Lock Final Version - Import Vote Data - Validate Vote Data - Calculate Ranking - Ranking Dashboard - Ranking History - Risk Alert - Risk Alert Detail - Series Dossier - Board Decision - Update Series Status - Full System Testing - Bug Fixing - Demo Data - Final Report / Slide

## Members
Member | Suggested Role | Assigned Count
Hiền | Project Leader / BA / Document | 0
Hào | Frontend Lead | 0
Dũng | Tester / Backend Lead | 0
Phát | Page Workspace / Integration | 0

## Jira Import
Issue Type | Summary | Description | Assignee | Priority | Sprint | Epic Name | Labels
Task | [Authentication] Login | Function ID: S1-F01 Sprint: Sprint 1 Description: User can log in using valid email and password |  | High | Sprint 1 | Authentication | authentication
Task | [Authentication] Logout | Function ID: S1-F02 Sprint: Sprint 1 Description: User can log out from the system |  | High | Sprint 1 | Authentication | authentication
Task | [Authorization] Role-based Dashboard | Function ID: S1-F03 Sprint: Sprint 1 Description: System redirects user to the correct dashboard based on role |  | High | Sprint 1 | Authorization | authorization
Task | [Administration] User Management | Function ID: S1-F04 Sprint: Sprint 1 Description: Admin can create, update, deactivate users |  | Medium | Sprint 1 | Administration | administration
Task | [Administration] Role Management | Function ID: S1-F05 Sprint: Sprint 1 Description: Admin can assign roles to users |  | Medium | Sprint 1 | Administration | administration
Task | [Series Proposal] Create Series Proposal | Function ID: S1-F06 Sprint: Sprint 1 Description: Mangaka can create a new series proposal |  | High | Sprint 1 | Series Proposal | series-proposal
Task | [Series Proposal] Edit Series Proposal | Function ID: S1-F07 Sprint: Sprint 1 Description: Mangaka can edit proposal before submission |  | Medium | Sprint 1 | Series Proposal | series-proposal
Task | [Series Proposal] Upload Sample Manuscript | Function ID: S1-F08 Sprint: Sprint 1 Description: Mangaka can upload sample manuscript for proposal |  | High | Sprint 1 | Series Proposal | series-proposal
Task | [Series Proposal] Submit Proposal | Function ID: S1-F09 Sprint: Sprint 1 Description: Proposal can be submitted for approval |  | High | Sprint 1 | Series Proposal | series-proposal
Task | [Proposal Approval] Proposal Review | Function ID: S1-F10 Sprint: Sprint 1 Description: Editor or Board can view proposal detail |  | High | Sprint 1 | Proposal Approval | proposal-approval
Task | [Proposal Approval] Approve / Reject Proposal | Function ID: S1-F11 Sprint: Sprint 1 Description: Board can approve or reject proposal |  | High | Sprint 1 | Proposal Approval | proposal-approval
Task | [Series Management] Create Series from Approved Proposal | Function ID: S1-F12 Sprint: Sprint 1 Description: System creates official series after approval |  | High | Sprint 1 | Series Management | series-management
Task | [Series Management] Series List | Function ID: S1-F13 Sprint: Sprint 1 Description: User can view list of series |  | High | Sprint 1 | Series Management | series-management
Task | [Series Management] Series Detail | Function ID: S1-F14 Sprint: Sprint 1 Description: User can view series information and related chapters |  | High | Sprint 1 | Series Management | series-management
Task | [Chapter Management] Create Chapter | Function ID: S1-F15 Sprint: Sprint 1 Description: Mangaka can create a chapter for an active series |  | High | Sprint 1 | Chapter Management | chapter-management
Task | [Chapter Management] Chapter List | Function ID: S1-F16 Sprint: Sprint 1 Description: User can view chapter list by series |  | High | Sprint 1 | Chapter Management | chapter-management
Task | [Chapter Management] Chapter Detail | Function ID: S1-F17 Sprint: Sprint 1 Description: User can view chapter progress, deadline and page list |  | High | Sprint 1 | Chapter Management | chapter-management
Task | [Page Management] Upload Manga Page | Function ID: S1-F18 Sprint: Sprint 1 Description: Mangaka can upload manga pages for a chapter |  | High | Sprint 1 | Page Management | page-management
Task | [Page Management] Page List | Function ID: S1-F19 Sprint: Sprint 1 Description: User can view pages inside a chapter |  | Medium | Sprint 1 | Page Management | page-management
Task | [Page Workspace] Open Page Workspace | Function ID: S2-F01 Sprint: Sprint 2 Description: Mangaka can open workspace for a selected page |  | High | Sprint 2 | Page Workspace | page-workspace
Task | [Page Workspace] Display Manga Page Canvas | Function ID: S2-F02 Sprint: Sprint 2 Description: System displays manga page on canvas |  | High | Sprint 2 | Page Workspace | page-workspace
Task | [Page Workspace] Zoom / Fit Page | Function ID: S2-F03 Sprint: Sprint 2 Description: User can zoom in, zoom out and fit page |  | Medium | Sprint 2 | Page Workspace | page-workspace
Task | [Region Segmentation] Draw Region | Function ID: S2-F04 Sprint: Sprint 2 Description: Mangaka can draw a rectangle region on the page |  | High | Sprint 2 | Region Segmentation | region-segmentation
Task | [Region Segmentation] Select Region Type | Function ID: S2-F05 Sprint: Sprint 2 Description: Mangaka can select type: panel, character, background, bubble |  | High | Sprint 2 | Region Segmentation | region-segmentation
Task | [Region Segmentation] Save Region Coordinates | Function ID: S2-F06 Sprint: Sprint 2 Description: System saves x, y, width, height and region type |  | High | Sprint 2 | Region Segmentation | region-segmentation
Task | [Region Segmentation] Edit / Delete Region | Function ID: S2-F07 Sprint: Sprint 2 Description: Mangaka can edit or delete a region |  | Medium | Sprint 2 | Region Segmentation | region-segmentation
Task | [AI Optional] AI Suggest Region | Function ID: S2-F08 Sprint: Sprint 2 Description: AI can suggest regions on page, optional |  | Low | Sprint 2 | AI Optional | ai-optional
Task | [Task Management] Create Task from Region | Function ID: S2-F09 Sprint: Sprint 2 Description: Mangaka can create task from selected region |  | High | Sprint 2 | Task Management | task-management
Task | [Task Management] Assign Task to Assistant | Function ID: S2-F10 Sprint: Sprint 2 Description: Mangaka can assign task to an Assistant |  | High | Sprint 2 | Task Management | task-management
Task | [Task Management] Task Detail | Function ID: S2-F11 Sprint: Sprint 2 Description: User can view task detail and region information |  | High | Sprint 2 | Task Management | task-management
Task | [Task Management] Task Board | Function ID: S2-F12 Sprint: Sprint 2 Description: User can view tasks by status on kanban board |  | Medium | Sprint 2 | Task Management | task-management
Task | [Task Management] My Assigned Tasks | Function ID: S2-F13 Sprint: Sprint 2 Description: Assistant can view tasks assigned to them |  | High | Sprint 2 | Task Management | task-management
Task | [Task Management] Task Status Tracking | Function ID: S2-F14 Sprint: Sprint 2 Description: System tracks Assigned, In Progress, Submitted, Revision, Approved |  | High | Sprint 2 | Task Management | task-management
Task | [Notification] Task Notification | Function ID: S2-F15 Sprint: Sprint 2 Description: Assistant receives notification when task is assigned |  | Medium | Sprint 2 | Notification | notification
Task | [Assistant Submission] View My Tasks | Function ID: S2-F16 Sprint: Sprint 2 Description: Assistant can view assigned task list |  | High | Sprint 2 | Assistant Submission | assistant-submission
Task | [Assistant Submission] View Task Detail | Function ID: S2-F17 Sprint: Sprint 2 Description: Assistant can view task instruction and deadline |  | High | Sprint 2 | Assistant Submission | assistant-submission
Task | [Assistant Submission] Download Reference File | Function ID: S2-F18 Sprint: Sprint 2 Description: Assistant can download page or reference files |  | Medium | Sprint 2 | Assistant Submission | assistant-submission
Task | [Assistant Submission] Upload Submission | Function ID: S2-F19 Sprint: Sprint 2 Description: Assistant can upload completed task file |  | High | Sprint 2 | Assistant Submission | assistant-submission
Task | [Assistant Submission] Add Submission Note | Function ID: S2-F20 Sprint: Sprint 2 Description: Assistant can add note when submitting |  | Medium | Sprint 2 | Assistant Submission | assistant-submission
Task | [Assistant Submission] Submission Version History | Function ID: S2-F21 Sprint: Sprint 2 Description: System stores multiple submission versions |  | Medium | Sprint 2 | Assistant Submission | assistant-submission
Task | [Notification] Submission Notification | Function ID: S2-F22 Sprint: Sprint 2 Description: Mangaka receives notification when submission is uploaded |  | Medium | Sprint 2 | Notification | notification
Task | [Mangaka Review] Pending Submission List | Function ID: S2-F23 Sprint: Sprint 2 Description: Mangaka can view submissions waiting for review |  | High | Sprint 2 | Mangaka Review | mangaka-review
Task | [Mangaka Review] Submission Preview | Function ID: S2-F24 Sprint: Sprint 2 Description: Mangaka can preview Assistant submission |  | High | Sprint 2 | Mangaka Review | mangaka-review
Task | [Mangaka Review] Compare Original / Submission | Function ID: S2-F25 Sprint: Sprint 2 Description: Mangaka can compare original page and submitted file |  | Medium | Sprint 2 | Mangaka Review | mangaka-review
Task | [Mangaka Review] Approve Submission | Function ID: S2-F26 Sprint: Sprint 2 Description: Mangaka can approve accepted submission |  | High | Sprint 2 | Mangaka Review | mangaka-review
Task | [Mangaka Review] Request Revision | Function ID: S2-F27 Sprint: Sprint 2 Description: Mangaka can request revision if submission is not accepted |  | High | Sprint 2 | Mangaka Review | mangaka-review
Task | [Mangaka Review] Review Comment | Function ID: S2-F28 Sprint: Sprint 2 Description: Mangaka must write comment when requesting revision |  | High | Sprint 2 | Mangaka Review | mangaka-review
Task | [Chapter Progress] Update Chapter Progress | Function ID: S2-F29 Sprint: Sprint 2 Description: System updates chapter progress after task approval |  | High | Sprint 2 | Chapter Progress | chapter-progress
Task | [Editor Review] Chapter Ready for Review List | Function ID: S2-F30 Sprint: Sprint 2 Description: Editor can view chapters ready for review |  | High | Sprint 2 | Editor Review | editor-review
Task | [Editor Review] Editor Review Screen | Function ID: S2-F31 Sprint: Sprint 2 Description: Editor can review chapter pages and manuscript |  | High | Sprint 2 | Editor Review | editor-review
Task | [Annotation] Add Annotation | Function ID: S2-F32 Sprint: Sprint 2 Description: Editor can add annotation on page |  | High | Sprint 2 | Annotation | annotation
Task | [Annotation] Annotation Type | Function ID: S2-F33 Sprint: Sprint 2 Description: Editor can classify annotation type |  | Medium | Sprint 2 | Annotation | annotation
Task | [Editor Review] Approve Chapter | Function ID: S2-F34 Sprint: Sprint 2 Description: Editor can approve reviewed chapter |  | High | Sprint 2 | Editor Review | editor-review
Task | [Editor Review] Send Revision to Mangaka | Function ID: S2-F35 Sprint: Sprint 2 Description: Editor can request Mangaka revision |  | High | Sprint 2 | Editor Review | editor-review
Task | [Editor Review] Review History | Function ID: S2-F36 Sprint: Sprint 2 Description: System stores editor review history |  | Medium | Sprint 2 | Editor Review | editor-review
Task | [Publishing] Publication Schedule | Function ID: S3-F01 Sprint: Sprint 3 Description: Board can create publication schedule |  | Medium | Sprint 3 | Publishing | publishing
Task | [Publishing] Final Approval | Function ID: S3-F02 Sprint: Sprint 3 Description: Board can final approve chapter |  | Medium | Sprint 3 | Publishing | publishing
Task | [Publishing] Lock Final Version | Function ID: S3-F03 Sprint: Sprint 3 Description: System locks final version after approval |  | Medium | Sprint 3 | Publishing | publishing
Task | [Voting] Import Vote Data | Function ID: S3-F04 Sprint: Sprint 3 Description: Board can import reader vote data |  | Medium | Sprint 3 | Voting | voting
Task | [Voting] Validate Vote Data | Function ID: S3-F05 Sprint: Sprint 3 Description: System validates vote data |  | Medium | Sprint 3 | Voting | voting
Task | [Ranking] Calculate Ranking | Function ID: S3-F06 Sprint: Sprint 3 Description: System calculates ranking by vote data |  | Medium | Sprint 3 | Ranking | ranking
Task | [Ranking] Ranking Dashboard | Function ID: S3-F07 Sprint: Sprint 3 Description: User can view ranking dashboard |  | Medium | Sprint 3 | Ranking | ranking
Task | [Ranking] Ranking History | Function ID: S3-F08 Sprint: Sprint 3 Description: User can view ranking history by issue |  | Low | Sprint 3 | Ranking | ranking
Task | [Risk Decision] Risk Alert | Function ID: S3-F09 Sprint: Sprint 3 Description: System creates alert when ranking is low |  | Medium | Sprint 3 | Risk Decision | risk-decision
Task | [Risk Decision] Risk Alert Detail | Function ID: S3-F10 Sprint: Sprint 3 Description: Board can view detail of ranking risk |  | Medium | Sprint 3 | Risk Decision | risk-decision
Task | [Risk Decision] Series Dossier | Function ID: S3-F11 Sprint: Sprint 3 Description: Board can view series dossier before decision |  | Medium | Sprint 3 | Risk Decision | risk-decision
Task | [Risk Decision] Board Decision | Function ID: S3-F12 Sprint: Sprint 3 Description: Board can choose Continue, Cancel, or Change Schedule |  | Medium | Sprint 3 | Risk Decision | risk-decision
Task | [Risk Decision] Update Series Status | Function ID: S3-F13 Sprint: Sprint 3 Description: System updates series status after board decision |  | Medium | Sprint 3 | Risk Decision | risk-decision
Task | [Testing] Full System Testing | Function ID: S3-F14 Sprint: Sprint 3 Description: Team tests the full end-to-end workflow |  | High | Sprint 3 | Testing | testing
Task | [Testing] Bug Fixing | Function ID: S3-F15 Sprint: Sprint 3 Description: Team fixes critical bugs before final demo |  | High | Sprint 3 | Testing | testing
Task | [Demo] Demo Data | Function ID: S3-F16 Sprint: Sprint 3 Description: Prepare accounts, series, chapters, pages, tasks, submissions, ranking data |  | High | Sprint 3 | Demo | demo
Task | [Documentation] Final Report / Slide | Function ID: S3-F17 Sprint: Sprint 3 Description: Complete final report and presentation slide |  | High | Sprint 3 | Documentation | documentation

## Lists
Status | Priority | Owner | Sprint
To Do | High | Hiền | Sprint 1
In Progress | Medium | Hào | Sprint 2
Code Review | Low | Dũng | Sprint 3
Testing |  | Phát
Done